## 400LSD Tier 1 Matrix (hidden)
400 LSD, CHICAGO, IL - 02/28/25
Floor | UNIT TYPE / TIER | T01 - AFFORDABLE |  | T01 - MARKET RATE |  | T02 - MARKET RATE |  | T03 - AFFORDABLE |  | T03 - MARKET RATE |  | T04 - MARKET RATE |  | T05 - MARKET RATE |  | T06 - AFFORDABLE |  | T06 - MARKET RATE |  | T07 - MARKET RATE |  | T08 - AFFORDABLE |  | T08 - MARKET RATE |  | T09 - MARKET RATE |  | T10 - MARKET RATE |  | T11 - AFFORDABLE |  | T11 - MARKET RATE |  | T12 - MARKET RATE |  | T14 - AFFORDABLE |  | T14 - MARKET RATE |  | Quantities |  | Kitchen Handles/Floor | Vanity Knobs/Floor
|  | STUDIO |  |  |  | 1 BEDROOM |  | 2 BEDROOM |  |  |  | STUDIO |  | STUDIO |  | 1 BEDROOM |  |  |  | 1 BEDROOM |  | STUDIO |  |  |  | 2 BEDROOM |  | 1 BEDROOM |  | 1 BEDROOM |  |  |  | 1 BEDROOM |  | 2 BEDROOM
FLOOR
43 | APARTMENT TOWER |  |  | 4301 |  | 4302 |  |  |  |  | 4303 |  | 4304 | 4305 |  |  |  | 4306 |  |  | 4307 |  |  | 4308 |  | 4309 |  | 4310 |  |  |  | 4311 |  | 4312 |  |  |  | 4314 |  | 43 | 13 | 41 | 61
42 |  |  |  |  | 4201 | 4202 |  |  |  | 4203 |  | 4204 |  | 4205 |  |  |  |  | 4206 | 4207 |  |  |  | 4208 |  | 4209 |  | 4210 |  |  |  | 4211 |  | 4212 |  |  |  | 4214 |  | 42 | 13 | 41 | 61
41 |  |  |  | 4101 |  |  | 4102 |  |  | 4103 |  | 4104 |  | 4105 |  |  |  | 4106 |  | 4107 |  |  |  |  | 4108 |  | 4109 | 4110 |  |  |  |  | 4111 | 4112 |  |  |  | 4114 |  | 41 | 13 | 41 | 61
40 |  |  |  | 4001 |  | 4002 |  |  |  | 4003 |  | 4004 |  | 4005 |  |  |  | 4006 |  | 4007 |  |  |  | 4008 |  | 4009 |  | 4010 |  |  |  | 4011 |  | 4012 |  |  |  | 4014 |  | 40 | 13 | 41 | 61
39 |  |  |  | 3901 |  |  | 3902 |  |  |  | 3903 | 3904 |  |  | 3905 |  |  | 3906 |  | 3907 |  |  |  | 3908 |  | 3909 |  | 3910 |  |  |  | 3911 |  |  | 3912 |  |  | 3914 |  | 39 | 13 | 41 | 61
38 |  |  |  | 3801 |  | 3802 |  |  |  | 3803 |  |  | 3804 | 3805 |  |  |  |  | 3806 | 3807 |  |  |  | 3808 |  |  | 3809 | 3810 |  |  |  | 3811 |  | 3812 |  |  |  | 3814 |  | 38 | 13 | 41 | 61
37 |  |  |  | 3701 |  | 3702 |  |  |  | 3703 |  | 3704 |  | 3705 |  |  |  | 3706 |  | 3707 |  |  |  | 3707 |  | 3709 |  | 3710 |  |  |  |  | 3711 | 3712 |  |  |  |  | 3714 | 37 | 13 | 41 | 61
36 |  |  |  | 3601 |  | 3602 |  |  |  |  | 3603 | 3604 |  | 3605 |  |  |  | 3606 |  | 3607 |  |  |  |  | 3608 | 3609 |  |  | 3610 |  |  | 3611 |  | 3612 |  |  |  | 3614 |  | 36 | 13 | 41 | 61
35 |  |  |  | 3501 |  |  | 3502 |  |  | 3503 |  | 3504 |  | 3505 |  |  |  | 3506 |  |  | 3507 |  |  | 3508 |  | 3509 |  | 3510 |  |  |  | 3511 |  | 3512 |  |  |  | 3514 |  | 35 | 13 | 41 | 61
34 |  |  |  | 3401 |  | 3402 |  |  |  | 3403 |  | 3404 |  | 3405 |  |  |  | 3406 |  | 3407 |  |  |  | 3408 |  | 3409 |  | 3410 |  |  |  | 3411 |  |  | 3412 |  |  |  | 3414 | 34 | 13 | 41 | 61
33 |  |  |  | 3301 |  | 3302 |  |  |  | 3303 |  |  | 3304 | 3305 |  |  |  | 3306 |  | 3307 |  |  |  | 3308 |  |  | 3309 |  | 3310 |  |  | 3311 |  | 3312 |  |  |  | 3314 |  | 33 | 13 | 41 | 61
32 |  |  |  | 3201 |  | 3202 |  |  |  |  | 3203 | 3204 |  |  | 3205 | 3206 |  |  |  | 3207 |  |  |  | 3208 |  | 3209 |  | 3210 |  |  | 3211 |  |  | 3212 |  |  |  | 3214 |  | 32 | 13 | 35 | 57
31 |  |  |  | 3101 |  | 3102 |  |  |  | 3103 |  | 3104 |  | 3105 |  | 3106 |  |  |  |  | 3107 |  |  |  | 3108 | 3109 |  | 3110 |  | 3111 |  |  |  | 3112 |  |  |  | 3114 |  | 31 | 13 | 35 | 57
30 |  |  |  | 3001 |  | 3002 |  |  |  | 3003 |  | 3004 |  | 3005 |  |  | 3006 |  |  | 3007 |  |  |  | 3008 |  | 3009 |  | 3010 |  | 3011 |  |  |  | 3012 |  |  |  | 3014 |  | 30 | 13 | 35 | 57
29 |  |  |  | 2901 |  | 2902 |  |  |  | 2903 |  | 2904 |  |  | 2905 | 2906 |  |  |  | 2907 |  |  |  | 2908 |  |  | 2909 | 2910 |  | 2911 |  |  |  | 2912 |  |  |  | 2914 |  | 29 | 13 | 35 | 57
28 |  |  |  | 2801 |  | 2802 |  |  |  | 2803 |  |  | 2804 | 2805 |  | 2806 |  |  |  | 2807 |  |  |  | 2808 |  | 2809 |  | 2810 |  |  | 2811 |  |  | 2812 |  |  |  |  | 2814 | 28 | 13 | 35 | 57
27 |  |  |  |  | 2701 | 2702 |  |  |  | 2703 |  | 2704 |  | 2705 |  | 2706 |  |  |  | 2707 |  |  |  | 2708 |  | 2709 |  |  | 2710 | 2711 |  |  |  |  | 2712 |  |  | 2714 |  | 27 | 13 | 35 | 57
26 |  |  |  | 2601 |  | 2602 |  |  |  | 2603 |  | 2604 |  | 2605 |  |  | 2606 |  |  | 2607 |  |  |  |  | 2608 | 2609 |  | 2610 |  | 2611 |  |  |  | 2612 |  |  |  | 2614 |  | 26 | 13 | 35 | 57
25 |  |  |  |  | 2501 | 2502 |  |  |  | 2503 |  | 2504 |  | 2505 |  | 2506 |  |  |  |  | 2507 |  |  | 2508 |  |  | 2509 | 2510 |  | 2511 |  |  |  | 2512 |  |  |  | 2514 |  | 25 | 13 | 35 | 57
24 |  | 2401 |  |  |  |  | 2402 |  |  | 2403 |  |  | 2404 | 2405 |  | 2406 |  |  |  | 2407 |  |  |  | 2408 |  | 2409 |  | 2410 |  |  | 2411 |  |  | 2412 |  |  |  |  | 2414 | 24 | 13 | 32 | 55
23 |  | 2301 |  |  |  | 2302 |  |  |  | 2303 |  | 2304 |  | 2305 |  | 2306 |  |  |  | 2307 |  | 2308 |  |  |  | 2309 |  |  | 2310 | 2311 |  |  |  | 2312 |  |  |  | 2314 |  | 23 | 13 | 29 | 53
22 |  | 2201 |  |  |  | 2202 |  |  |  |  | 2203 | 2204 |  | 2205 |  | 2206 |  |  |  | 2207 |  |  | 2208 |  |  | 2209 |  | 2210 |  | 2211 |  |  |  |  | 2212 | 2214 |  |  |  | 22 | 13 | 24 | 52
21 |  |  | 2101 |  |  | 2102 |  |  |  | 2103 |  | 2104 |  | 2105 |  |  | 2106 |  |  | 2107 |  | 2108 |  |  |  |  | 2109 | 2110 |  | 2111 |  |  |  | 2112 |  | 2114 |  |  |  | 21 | 13 | 24 | 52
20 |  | 2001 |  |  |  | 2002 |  |  |  | 2003 |  | 2004 |  |  | 2005 | 2006 |  |  |  | 2007 |  |  | 2008 |  |  | 2009 |  | 2010 |  |  | 2011 |  |  | 2012 |  | 2014 |  |  |  | 20 | 13 | 24 | 52
19 |  | 1901 |  |  |  | 1902 |  |  |  | 1903 |  | 1904 |  | 1905 |  | 1906 |  |  |  |  | 1907 | 1908 |  |  |  | 1909 |  |  | 1910 | 1911 |  |  |  |  | 1912 |  | 1914 |  |  | 19 | 13 | 24 | 52
18 |  | 1801 |  |  |  | 1802 |  |  |  |  | 1803 | 1804 |  |  | 1805 |  | 1806 |  |  | 1807 |  | 1808 |  |  |  | 1809 |  | 1810 |  | 1811 |  |  |  | 1812 |  | 1814 |  |  |  | 18 | 13 | 24 | 52
17 |  | 1701 |  |  |  |  | 1702 |  |  | 1703 |  |  | 1704 | 1705 |  | 1706 |  |  |  | 1707 |  | 1708 |  |  |  | 1709 |  | 1710 |  | 1711 |  |  |  | 1712 |  | 1714 |  |  |  | 17 | 13 | 24 | 52
16 |  |  | 1601 |  |  | 1602 |  |  |  | 1603 |  | 1604 |  | 1605 |  | 1606 |  |  |  | 1607 |  | 1608 |  |  |  | 1609 |  |  | 1610 | 1611 |  |  |  | 1612 |  | 1614 |  |  |  | 16 | 13 | 24 | 52
15 |  | 1501 |  |  |  |  | 1502 |  |  | 1503 |  | 1504 |  | 1505 |  | 1506 |  |  |  | 1507 |  | 1508 |  |  |  | 1509 |  | 1510 |  | 1511 |  |  |  | 1512 |  | 1514 |  |  |  | 15 | 13 | 24 | 52
14 |  | 1401 |  |  |  | 1402 |  |  |  | 1403 |  | 1404 |  | 1405 |  | 1406 |  |  |  | 1407 |  |  | 1408 |  |  | 1409 |  | 1410 |  | 1411 |  |  |  |  | 1412 | 1414 |  |  |  | 14 | 13 | 24 | 52
12 |  |  | 1201 |  |  | 1202 |  |  |  | 1203 |  | 1204 |  | 1205 |  | 1206 |  |  |  |  | 1207 | 1208 |  |  |  | 1209 |  | 1210 |  | 1211 |  |  |  | 1212 |  | 1214 |  |  |  | 12 | 13 | 24 | 52
11 |  | 1101 |  |  |  | 1102 |  | 1103 |  |  |  | 1104 |  | 1105 |  |  | 1106 |  |  | 1107 |  | 1108 |  |  |  | 1109 |  | 1110 |  | 1111 |  |  |  | 1112 |  |  | 1114 |  |  | 11 | 13 | 21 | 51
10 |  | 1001 |  |  |  | 1002 |  |  | 1003 |  |  |  | 1004 |  | 1005 | 1006 |  |  |  | 1007 |  | 1008 |  |  |  | 1009 |  |  | 1010 | 1011 |  |  |  | 1012 |  | 1014 |  |  |  | 10 | 13 | 21 | 51
9 |  |  | 901 |  |  | 902 |  | 903 |  |  |  | 904 |  | 905 |  | 906 |  |  |  |  | 907 | 908 |  |  |  | 909 |  | 910 |  | 911 |  |  |  |  | 912 | 914 |  |  |  | 9 | 13 | 21 | 51
8 |  | 801 |  |  |  | 802 |  | 803 |  |  |  | 804 |  | 805 |  | 806 |  |  |  | 807 |  | 808 |  |  |  |  | 809 |  | 810 | 811 |  |  |  | 812 |  | 814 |  |  |  | 8 | 13 | 21 | 51
7 |  |  | 701 |  |  | 702 |  | 703 |  |  |  | 704 |  | 705 |  | 706 |  |  |  | 707 |  | 708 |  |  |  | 709 |  | 710 |  |  | 711 |  |  | 712 |  | 714 |  |  |  | 7 | 13 | 21 | 51
6 |  | 601 |  |  |  | 602 |  | 603 |  |  |  |  | 604 | 605 |  | 606 |  |  |  |  | 607 | 608 |  |  |  | 609 |  | 610 |  | 611 |  |  |  | 612 |  |  | 614 |  |  | 6 | 13 | 21 | 51
5 |  | 501 |  |  |  | 502 |  |  | 503 |  |  | 504 |  |  | 505 |  | 506 |  |  | 507 |  | 508 |  |  |  |  | 509 | 510 |  | 511 |  |  |  |  | 512 | 514 |  |  |  | 5 | 13 | 21 | 51
4 |  | 401 |  |  |  |  | 402 | 403 |  |  |  | 404 |  | 405 |  | 406 |  |  |  | 407 |  |  | 408 |  |  | 409 |  | 410 |  | 411 |  |  |  | 412 |  | 414 |  |  |  | 4 | 13 | 21 | 51
3 |  | 301 |  |  |  | 302 |  | 303 |  |  |  | 304 |  |  | 305 | 306 |  |  |  | 307 |  | 308 |  |  |  | 309 |  | 310 |  |  | 311 |  |  | 312 |  |  | 314 |  |  | 3 | 13 | 21 | 51
2 | AMENITY | [38 empty] | 2 | 0
1 | LOBBY | [38 empty] | 1 | 0
# Of Units |  | 16 | 5 | 16 | 3 | 33 | 7 | 7 | 2 | 25 | 6 | 32 | 8 | 32 | 8 | 23 | 6 | 9 | 2 | 32 | 8 | 16 | 4 | 16 | 4 | 32 | 8 | 32 | 8 | 23 | 6 | 9 | 2 | 32 | 8 | 15 | 4 | 17 | 4 | TOTAL # UNITS | 520
# Of Type B |  | 16 | 0 | 16 | 0 | 33 | 0 | 7 | 0 | 25 | 0 | 32 | 0 | 32 | 0 | 23 | 0 | 9 | 0 | 32 | 0 | 16 | 0 | 16 | 0 | 32 | 0 | 32 | 0 | 23 | 0 | 9 | 0 | 32 | 0 | 15 | 0 | 17 | 0 | TOTAL TYPE B UNITS | 417
# Of Type A |  | 0 | 5 | 0 | 3 | 0 | 7 | 0 | 2 | 0 | 6 | 0 | 8 | 0 | 8 | 0 | 6 | 0 | 2 | 0 | 8 | 0 | 4 | 0 | 4 | 0 | 8 | 0 | 8 | 0 | 6 | 0 | 2 | 0 | 8 | 0 | 4 | 0 | 4 | TOTAL TYPE A UNITS | 103
UNIT TYPE |  | T01 - AFFORDABLE |  | T01 - MARKET RATE |  | T02 - MARKET RATE |  | T03 - AFFORDABLE |  | T03 - MARKET RATE |  | T04 - MARKET RATE |  | T05 - MARKET RATE |  | T06 - AFFORDABLE |  | T06 - MARKET RATE |  | T07 - MARKET RATE |  | T08 - AFFORDABLE |  | T08 - MARKET RATE |  | T09 - MARKET RATE |  | T10 - MARKET RATE |  | T11 - AFFORDABLE |  | T11 - MARKET RATE |  | T12 - MARKET RATE |  | T14 - AFFORDABLE |  | T14 - MARKET RATE
KITCHEN TYPE |  | K01.TI - AFF | K01.T1(A) - AFF | K01.T1-MR | K01.T1(A)-MR | K02.T1-MR | K02.T1(A)-MR | K03.T1-AFF | K03.T1(A)-AFF | K03.T1-MR | K03.T1(A)-MR | K04.T1-MR | K04.T1(A)-MR | K05.T1-MR | K05.T1(A)-MR | K06.T1-AFF | K06.T1(A)-AFF | K06.T1-MR | K06.T1(A)-MR | K07.T1-MR | K07.T1(A)-MR | K08.T1-AFF | K08.T1(A)-AFF | K08.T1-MR | K08.T1(A)-MR | K09.T1-MR | K09.T1(A)-MR | K10.T1-MR | K10.T1(A)-MR | K11.T1-AFF | K11.T1(A)-AFF | K11.T1-MR | K11.T1(A)-MR | K12.T1-MR | K12.T1(A)-MR | K14.T1-AFF | K14.T1(A)-AFF | K14.T1-MR | K14.T1(A)-MR
PRIMARY BATH TYPE |  | T1(AFF)_36-PRIM | T1(AFF)_36-PRIM | T1(MR)_36-PRIM | T1(MR)_36-PRIM | T1(MR)_48-PRIM | T1(MR)_48-PRIM | T1(AFF)_60-PRIM | T1(AFF)_60-PRIM | T1(MR)_60-PRIM | T1(MR)_60-PRIM | T1(MR)_36-PRIM | T1(MR)_36-PRIM | T1(MR)_36-PRIM | T1(MR)_36-PRIM | T1(AFF)_36-PRIM | T1(AFF)_36-PRIM | T1(MR)_36-PRIM | T1(MR)_36-PRIM | T1(MR)_36-PRIM | T1(MR)_36-PRIM | T1(AFF)_36-PRIM | T1(AFF)_36-PRIM | T1(MR)_36-PRIM | T1(MR)_36-PRIM | T1(MR)_60-PRIM | T1(MR)_60-PRIM | T1(MR)_36-PRIM | T1(MR)_36-PRIM | T1(AFF)_36-PRIM | T1(AFF)_36-PRIM | T1(MR)_36-PRIM | T1(MR)_36-PRIM | T1(MR)_36-PRIM | T1(MR)_36-PRIM | T1(AFF)_60-PRIM | T1(AFF)_60-PRIM | T1(MR)_60-PRIM | T1(MR)_60-PRIM
SECONDARY BATH TYPE | [7 empty] | T1(AFF)_36-SEC | T1(AFF)_36-SEC | T1(MR)_36-SEC | T1(MR)_36-SEC | [14 empty] | T1(MR)_36-SEC | T1(MR)_36-SEC | [8 empty] | T1(AFF)_36-SEC | T1(AFF)_36-SEC | T1(MR)_36-SEC | T1(MR)_36-SEC
WARDROBE TYPE |  | WAR01.T1-AFF | WAR01.T1-AFF | WAR01.T1-MR | WAR01.T1-MR |  |  | WAR03.T1-AFF | WAR03.T1-AFF | WAR03.T1-MR | WAR03.T1-MR | [18 empty] | WAR11.T1-AFF | WAR11.T1-AFF | WAR11.T1-MR | WAR11.T1-MR
HANDLES QUANTITIES
KITCHEN HANDLE QTY |  | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 5 | 5
VANITY KNOB QTY |  | 2 | 2 | 4 | 4 | 4 | 4 | 6 | 6 | 7 | 7 | 4 | 4 | 4 | 4 | 2 | 2 | 4 | 4 | 4 | 4 | 2 | 2 | 4 | 4 | 7 | 7 | 4 | 4 | 2 | 2 | 4 | 4 | 4 | 4 | 6 | 6 | 7 | 7
KITCHEN QUANTITIES
KITCHENS
| K01.T1-AFF | 16 | [37 empty] | K01.T1-AFF | 16
| K03.T1-AFF | [6 empty] | 7 | [31 empty] | K03.T1-AFF | 7
| K06.T1-AFF | [14 empty] | 23 | [23 empty] | K06.T1-AFF | 23
| K08.T1-AFF | [20 empty] | 16 | [17 empty] | K08.T1-AFF | 16
| K11.T1-AFF | [28 empty] | 23 | [9 empty] | K11.T1-AFF | 23
| K14.T1-AFF | [34 empty] | 15 |  |  |  | K14.T1-AFF | 15
| K01.T1(A)-AFF |  | 5 | [36 empty] | K01.T1(A)-AFF | 5
| K03.T1(A)-AFF | [7 empty] | 2 | [30 empty] | K03.T1(A)-AFF | 2
| K06.T1(A)-AFF | [15 empty] | 6 | [22 empty] | K06.T1(A)-AFF | 6
| K08.T1(A)-AFF | [21 empty] | 4 | [16 empty] | K08.T1(A)-AFF | 4
| K11.T1(A)-AFF | [29 empty] | 6 | [8 empty] | K11.T1(A)-AFF | 6
| K14.T1(A)-AFF | [35 empty] | 4 |  |  | K14.T1(A)-AFF | 4
| K01.T1-MR |  |  | 16 | [35 empty] | K01.T1-MR | 16
| K02.T1-MR |  |  |  |  | 33 | [33 empty] | K02.T1-MR | 33
| K03.T1-MR | [8 empty] | 25 | [29 empty] | K03.T1-MR | 25
| K04.T1-MR | [10 empty] | 32 | [27 empty] | K04.T1-MR | 32
| K05.T1-MR | [12 empty] | 32 | [25 empty] | K05.T1-MR | 32
| K06.T1-MR | [16 empty] | 9 | [21 empty] | K06.T1-MR | 9
| K07.T1-MR | [18 empty] | 32 | [19 empty] | K07.T1-MR | 32
| K08.T1-MR | [22 empty] | 16 | [15 empty] | K08.T1-MR | 16
| K09.T1-MR | [24 empty] | 32 | [13 empty] | K09.T1-MR | 32
| K10.T1-MR | [26 empty] | 32 | [11 empty] | K10.T1-MR | 32
| K11.T1-MR | [30 empty] | 9 | [7 empty] | K11.T1-MR | 9
| K12.T1-MR | [32 empty] | 32 | [5 empty] | K12.T1-MR | 32
| K14.T1-MR | [36 empty] | 17 |  | K14.T1-MR | 17
| K01.T1(A)-MR |  |  |  | 3 | [34 empty] | K01.T1(A)-MR | 3
| K02.T1(A)-MR | [5 empty] | 7 | [32 empty] | K02.T1(A)-MR | 7
| K03.T1(A)-MR | [9 empty] | 6 | [28 empty] | K03.T1(A)-MR | 6
| K04.T1(A)-MR | [11 empty] | 8 | [26 empty] | K04.T1(A)-MR | 8
| K05.T1(A)-MR | [13 empty] | 8 | [24 empty] | K05.T1(A)-MR | 8
| K06.T1(A)-MR | [17 empty] | 2 | [20 empty] | K06.T1(A)-MR | 2
| K07.T1(A)-MR | [19 empty] | 8 | [18 empty] | K07.T1(A)-MR | 8
| K08.T1(A)-MR | [23 empty] | 4 | [14 empty] | K08.T1(A)-MR | 4
| K09.T1(A)-MR | [25 empty] | 8 | [12 empty] | K09.T1(A)-MR | 8
| K10.T1(A)-MR | [27 empty] | 8 | [10 empty] | K10.T1(A)-MR | 8
| K11.T1(A)-MR | [31 empty] | 2 | [6 empty] | K11.T1(A)-MR | 2
| K12.T1(A)-MR | [33 empty] | 8 |  |  |  |  | K12.T1(A)-MR | 8
| K14.T1(A)-MR | [37 empty] | 4 | K14.T1(A)-MR | 4
[40 empty] | TOTAL KITCHENS | 520
VANITY QUANTITIES
VANITIES
| T1(AFF)_36-PRIM | 16 | 5 | [12 empty] | 23 | 6 |  |  |  |  | 16 | 4 | [6 empty] | 23 | 6 | [8 empty] | T1(AFF)_36-PRIM | 99
| T1(AFF)_60-PRIM | [6 empty] | 7 | 2 | [26 empty] | 15 | 4 |  |  | T1(AFF)_60-PRIM | 28
| T1(AFF)_36-SEC | [6 empty] | 7 | 2 | [26 empty] | 15 | 4 |  |  | T1(AFF)_36-SEC | 28
| T1(MR)_36-PRIM |  |  | 16 | 3 | [6 empty] | 32 | 8 | 32 | 8 |  |  | 9 | 2 | 32 | 8 |  |  | 16 | 4 |  |  | 32 | 8 |  |  | 9 | 2 | 32 | 8 |  |  |  |  | T1(MR)_36-PRIM | 261
| T1(MR)_48-PRIM |  |  |  |  | 33 | 7 | [32 empty] | T1(MR)_48-PRIM | 40
| T1(MR)_60-PRIM | [8 empty] | 25 | 6 | [14 empty] | 32 | 8 | [10 empty] | 17 | 4 | T1(MR)_60-PRIM | 92
| T1(MR)_36-SEC | [8 empty] | 25 | 6 | [14 empty] | 32 | 8 | [10 empty] | 17 | 4 | T1(MR)_36-SEC | 92
[40 empty] | TOTAL VANITIES | 640
WARDROBE QUANTITIES
WARDROBES
| WAR01.T1-AFF | 16 | 5 | [36 empty] | WAR01.T1-AFF | 21
| WAR03.T1-AFF | [6 empty] | 7 | 2 | [30 empty] | WAR03.T1-AFF | 9
| WAR11.T1-AFF | [28 empty] | 23 | 6 | [8 empty] | WAR11.T1-AFF | 29
| WAR01.T1-MR |  |  | 16 | 3 | [34 empty] | WAR01.T1-MR | 19
| WAR03.T1-MR | [8 empty] | 25 | 6 | [28 empty] | WAR03.T1-MR | 31
| WAR11.T1-MR | [30 empty] | 9 | 2 | [6 empty] | WAR11.T1-MR | 11
[40 empty] | TOTAL WARDROBES | 120
HANDLES QUANTITIES
HANDLES
| T1-K18-HANDLE |  |  | 48 | 9 | 99 | 21 |  |  | 75 | 18 | 96 | 24 | 96 | 24 |  |  | 27 | 6 | 96 | 24 |  |  | 48 | 12 | 96 | 24 | 96 | 24 |  |  | 27 | 6 | 96 | 24 |  |  | 85 | 20 | T1-K18-HANDLE | 1221
| T1-W18-HANDLE | 64 | 20 | 64 | 12 |  |  | 14 | 4 | 50 | 12 | [18 empty] | 46 | 12 | 18 | 4 | [6 empty] | T1-W18-HANDLE | 320
| T1-V-HANDLE | 32 | 10 | 64 | 12 | 132 | 28 | 42 | 12 | 175 | 42 | 128 | 32 | 128 | 32 | 46 | 12 | 36 | 8 | 128 | 32 | 32 | 8 | 64 | 16 | 224 | 56 | 128 | 32 | 46 | 12 | 36 | 8 | 128 | 32 | 90 | 24 | 119 | 28 | T1-V-HANDLE | 2214
[40 empty] | TOTAL HANDLES | 3755
[40 empty] | MR UNITS | 393
[40 empty] | AFF UNITS | 127

## 400LSD T1 (Condensed Matrix) (hidden)
400 LSD TIER 1 Compressed Unit Matrix,
Floor | UNIT TYPE / TIER | T01 | T02 | T03 | T04 | T05 | T06 | T07 | T08 | T09 | T10 | T11 | T12 | T14 | Quantities |  | Install Start
|  | STUDIO | 1 BEDROOM | 2 BEDROOM | STUDIO | STUDIO | 1 BEDROOM | 1 BEDROOM | STUDIO | 2 BEDROOM | 1 BEDROOM | 1 BEDROOM | 1 BEDROOM | 2 BEDROOM |  |  | DATE
FLOOR
43 | TIER 1 - APARTMENT TOWER | 4301-MR | 4302-MR | 4304-MR(A) | 4304-MR(A) | 4305-MR | 4306-MR | 4307-MR(A) | 4308-MR | 4309-MR | 4310-MR | 4311-MR | 4312-MR | 4314-MR | 43 | 13 | 2026-05-18
42 |  | 4201-MR(A) | 4202-MR | 4203-MR | 4204-MR | 4205-MR | 4206-MR(A) | 4207-MR | 4208-MR | 4209-MR | 4210-MR | 4211-MR | 4212-MR | 4214-MR | 42 | 13 | 2026-05-11
41 |  | 4101-MR | 4102-MR(A) | 4103-MR | 4104-MR | 4105-MR | 4106-MR | 4107-MR | 4108-MR(A) | 4109-MR(A) | 4110-MR | 4111-MR(A) | 4112-MR | 4114-MR | 41 | 13 | 2026-05-04
40 |  | 4001-MR | 4002-MR | 4003-MR | 4004-MR | 4005-MR | 4006-MR | 4007-MR | 4008-MR | 4009-MR | 4010-MR | 4011-MR | 4012-MR | 4014-MR | 40 | 13 | 2026-04-27
39 |  | 3901-MR | 3902-MR(A) | 3903-MR(A) | 3904-MR | 3905-MR(A) | 3906-MR | 3907-MR | 3908-MR | 3909-MR | 3910-MR | 3911-MR | 3912-MR(A) | 3914-MR | 39 | 13 | 2026-04-20
38 |  | 3801-MR | 3802-MR | 3803-MR | 3804-MR(A) | 3805-MR | 3806-MR(A) | 3807-MR | 3808-MR | 3809-MR(A) | 3810-MR | 3811-MR | 3812-MR | 3814-MR | 38 | 13 | 2026-04-13
37 |  | 3701-MR | 3702-MR | 3703-MR | 3704-MR | 3705-MR | 3706-MR | 3707-MR | 3707-MR | 3709-MR | 3710-MR | 3711-MR(A) | 3712-MR | 3714-MR(A) | 37 | 13 | 2026-04-06
36 |  | 3601-MR | 3602-MR | 3603-MR(A) | 3604-MR | 3605-MR | 3606-MR | 3607-MR | 3608-MR(A) | 3609-MR | 3610-MR(A) | 3611-MR | 3612-MR | 3614-MR | 36 | 13 | 2026-03-30
35 |  | 3501-MR | 3502-MR(A) | 3503-MR | 3504-MR | 3505-MR | 3506-MR | 3507-MR(A) | 3508-MR | 3509-MR | 3510-MR | 3511-MR | 3512-MR | 3514-MR | 35 | 13 | 2026-03-23
34 |  | 3401-MR | 3402-MR | 3403-MR | 3404-MR | 3405-MR | 3406-MR | 3407-MR | 3408-MR | 3409-MR | 3410-MR | 3411-MR | 3412-MR(A) | 3414-MR(A) | 34 | 13 | 2026-03-16
33 |  | 3301-MR | 3302-MR | 3303-MR | 3304-MR(A) | 3305-MR | 3306-MR | 3307-MR | 3308-MR | 3309-MR(A) | 3310-MR(A) | 3311-MR | 3312-MR | 3314-MR | 33 | 13 | 2026-03-09
32 |  | 3201-MR | 3202-MR | 3203-MR(A) | 3204-MR | 3205-MR(A) | 3206-AFF(B) | 3207-MR | 3208-MR | 3209-MR | 3210-MR | 3211-AFF(A) | 3212-MR | 3214-MR | 32 | 13 | 2026-03-02
31 |  | 3101-MR | 3102-MR | 3103-MR | 3104-MR | 3105-MR | 3106-AFF(B) | 3107-MR(A) | 3108-MR(A) | 3109-MR | 3110-MR | 3111-AFF(B) | 3112-MR | 3114-MR | 31 | 13 | 2026-02-23
30 |  | 3001-MR | 3002-MR | 3003-MR | 3004-MR | 3005-MR | 3006-AFF(A) | 3007-MR | 3008-MR | 3009-MR | 3010-MR | 3011-AFF(B) | 3012-MR | 3014-MR | 30 | 13 | 2026-02-16
29 |  | 2901-MR | 2902-MR | 2903-MR | 2904-MR | 2905-MR(A) | 2906-AFF(B) | 2907-MR | 2908-MR | 2909-MR(A) | 2910-MR | 2911-AFF(B) | 2912-MR | 2914-MR | 29 | 13 | 2026-02-09
28 |  | 2801-MR | 2802-MR | 2803-MR | 2804-MR(A) | 2805-MR | 2806-AFF(B) | 2807-MR | 2808-MR | 2809-MR | 2810-MR | 2811-AFF(A) | 2812-MR | 2814-MR(A) | 28 | 13 | 2026-02-02
27 |  | 2701-MR(A) | 2702-MR | 2703-MR | 2704-MR | 2705-MR | 2706-AFF(B) | 2707-MR | 2708-MR | 2709-MR | 2710-MR(A) | 2711-AFF(B) | 2712-MR(A) | 2714-MR | 27 | 13 | 2026-01-26
26 |  | 2601-MR | 2602-MR | 2603-MR | 2604-MR | 2605-MR | 2606-AFF(A) | 2607-MR | 2608-MR(A) | 2609-MR | 2610-MR | 2611-AFF(B) | 2612-MR | 2614-MR | 26 | 13 | 2026-01-19
25 |  | 2501-MR(A) | 2502-MR | 2503-MR | 2504-MR | 2505-MR | 2506-AFF(B) | 2507-MR(A) | 2508-MR | 2509-MR(A) | 2510-MR | 2511-AFF(B) | 2512-MR | 2514-MR | 25 | 13 | 2026-01-12
24 |  | 2401-AFF(B) | 2402-MR(A) | 2403-MR | 2404-MR(A) | 2405-MR | 2406-AFF(B) | 2407-MR | 2408-MR | 2409-MR | 2410-MR | 2411-AFF(A) | 2412-MR | 2414-MR(A) | 24 | 13 | 2026-01-05
23 |  | 2301-AFF(B) | 2302-MR | 2303-MR | 2304-MR | 2305-MR | 2306-AFF(B) | 2307-MR | 2308-AFF(B) | 2309-MR | 2310-MR(A) | 2311-AFF(B) | 2312-MR | 2314-MR | 23 | 13 | 2025-12-29
22 |  | 2201-AFF(B) | 2202-MR | 2203-MR(A) | 2204-MR | 2205-MR | 2206-AFF(B) | 2207-MR | 2208-AFF(A) | 2209-MR | 2210-MR | 2211-AFF(B) | 2212-MR(A) | 2214-AFF(B) | 22 | 13 | 2025-12-22
21 |  | 2101-AFF(A) | 2102-MR | 2103-MR | 2104-MR | 2105-MR | 2106-AFF(A) | 2107-MR | 2108-AFF(B) | 2109-MR(A) | 2110-MR | 2111-AFF(B) | 2112-MR | 2114-AFF(B) | 21 | 13 | 2025-12-15
20 |  | 2001-AFF(B) | 2002-MR | 2003-MR | 2004-MR | 2005-MR(A) | 2006-AFF(B) | 2007-MR | 2008-AFF(A) | 2009-MR | 2010-MR | 2011-AFF(A) | 2012-MR | 2014-AFF(B) | 20 | 13 | 2025-12-08
19 |  | 1901-AFF(B) | 1902-MR | 1903-MR | 1904-MR | 1905-MR | 1906-AFF(B) | 1907-MR(A) | 1908-AFF(B) | 1909-MR | 1910-MR(A) | 1911-AFF(B) | 1912-MR(A) | 1914-AFF(A) | 19 | 13 | HEAT TEMP FLOOR
18 |  | 1801-AFF(B) | 1802-MR | 1803-MR(A) | 1804-MR | 1805-MR(A) | 1806-AFF(A) | 1807-MR | 1808-AFF(B) | 1809-MR | 1810-MR | 1811-AFF(B) | 1812-MR | 1814-AFF(B) | 18 | 13 | 2025-12-01
17 |  | 1701-AFF(B) | 1702-MR(A) | 1703-MR | 1704-MR(A) | 1705-MR | 1706-AFF(B) | 1707-MR | 1708-AFF(B) | 1709-MR | 1710-MR | 1711-AFF(B) | 1712-MR | 1714-AFF(B) | 17 | 13 | 2025-11-24
16 |  | 1601-AFF(A) | 1602-MR | 1603-MR | 1604-MR | 1605-MR | 1606-AFF(B) | 1607-MR | 1608-AFF(B) | 1609-MR | 1610-MR(A) | 1611-AFF(B) | 1612-MR | 1614-AFF(B) | 16 | 13 | 2025-11-17
15 |  | 1501-AFF(B) | 1502-MR(A) | 1503-MR | 1504-MR | 1505-MR | 1506-AFF(B) | 1507-MR | 1508-AFF(B) | 1509-MR | 1510-MR | 1511-AFF(B) | 1512-MR | 1514-AFF(B) | 15 | 13 | 2025-11-10
14 |  | 1401-AFF(B) | 1402-MR | 1403-MR | 1404-MR | 1405-MR | 1406-AFF(B) | 1407-MR | 1408-AFF(A) | 1409-MR | 1410-MR | 1411-AFF(B) | 1412-MR(A) | 1414-AFF(B) | 14 | 13 | 2025-11-03
12 |  | 1201-AFF(A) | 1202-MR | 1203-MR | 1204-MR | 1205-MR | 1206-AFF(B) | 1207-MR(A) | 1208-AFF(B) | 1209-MR | 1210-MR | 1211-AFF(B) | 1212-MR | 1214-AFF(B) | 12 | 13 | 2025-10-27
11 |  | 1101-AFF(B) | 1102-MR | 1103-AFF(B) | 1104-MR | 1105-MR | 1106-AFF(A) | 1107-MR | 1108-AFF(B) | 1109-MR | 1110-MR | 1111-AFF(B) | 1112-MR | 1114-AFF(A) | 11 | 13 | 2025-10-20
10 |  | 1001-AFF(B) | 1002-MR | 1003-AFF(A) | 1004-MR(A) | 1005-MR(A) | 1006-AFF(B) | 1007-MR | 1008-AFF(B) | 1009-MR | 1010-MR(A) | 1011-AFF(B) | 1012-MR | 1014-AFF(B) | 10 | 13 | HEAT TEMP FLOOR
9 |  | 901-AFF(A) | 902-MR | 903-AFF(B) | 904-MR | 905-MR | 906-AFF(B) | 907-MR(A) | 908-AFF(B) | 909-MR | 910-MR | 911-AFF(B) | 912-MR(A) | 914-AFF(B) | 9 | 13 | 2025-10-13 | `
8 |  | 801-AFF(B) | 802-MR | 803-AFF(B) | 804-MR | 805-MR | 806-AFF(B) | 807-MR | 808-AFF(B) | 809-MR(A) | 810-MR(A) | 811-AFF(B) | 812-MR | 814-AFF(B) | 8 | 13 | 2025-10-06
7 |  | 701-AFF(A) | 702-MR | 703-AFF(B) | 704-MR | 705-MR | 706-AFF(B) | 707-MR | 708-AFF(B) | 709-MR | 710-MR | 711-AFF(A) | 712-MR | 714-AFF(B) | 7 | 13 | 2025-09-29
6 |  | 601-AFF(B) | 602-MR | 603-AFF(B) | 604-MR(A) | 605-MR | 606-AFF(B) | 607-MR(A) | 608-AFF(B) | 609-MR | 610-MR | 611-AFF(B) | 612-MR | 614-AFF(A) | 6 | 13 | 2025-09-22 | `
5 |  | 501-AFF(B) | 502-MR | 503-AFF(A) | 504-MR | 505-MR(A) | 506-AFF(A) | 507-MR | 508-AFF(B) | 509-MR(A) | 510-MR | 511-AFF(B) | 512-MR(A) | 514-AFF(B) | 5 | 13 | 2025-09-15
4 |  | 401-AFF(B) | 402-MR(A) | 403-AFF(B) | 404-MR | 405-MR | 406-AFF(B) | 407-MR | 408-AFF(A) | 409-MR | 410-MR | 411-AFF(B) | 412-MR | 414-AFF(B) | 4 | 13 | 2025-09-08
3 |  | 301-AFF(B) | 302-MR | 303-AFF(B) | 304-MR | 305-MR(A) | 306-AFF(B) | 307-MR | 308-AFF(B) | 309-MR | 310-MR | 311-AFF(A) | 312-MR | 314-AFF(A) | 3 | 13 | 2025-09-01
2 | AMENITY | [13 empty] | 2 | 0
1 | LOBBY | [13 empty] | 1 | 0
# Of Units |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TOTAL # UNITS | 520
# Of Type B |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TOTAL TYPE B UNITS | 0
# Of Type A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TOTAL TYPE A UNITS | 0
UNIT TYPE |  | T01 | T02 | T03 | T04 | T05 | T06 | T07 | T08 | T09 | T10 | T11 | T12 | T14
Formulas:
Install Start = [Install Start, row below]+7

## OMM_Overall Container Matrix
Example: Alpi slip | OPTIMA-CONTAINER SCHEDULE
#VALUE! | FULL SHIPPING LOGOISTICS | [8 empty] | Date: | 2026-08-11 |  | : Week 33
| FRM | FRM |  | TASK |  | FRM | FRM | FRM |  |  | FROMULA |  | TASK | FRM |  |  | TASK |  | TASK |  | FRM | TASK | TASK | FRM |  |  | TASK | FRM | TASK |  |  |  | FRM | FRM | TASK | TASK | TASK |  | FRM | FRM
| CONT. STATUS |  |  | LOADING SEQUENCE FR. FI (CTN. INFO) | [7 empty] | LOADED |  | SEA FREIGHT SHIPPED (1ST LEG) |  |  |  | SEA (2ND LEG) |  |  |  |  | TRAIN (3RD LEG) | [5 empty] | TRUCKING (4TH LEG) | [5 empty] | PROJECT STATUS | [5 empty] | MISC NOTES
Horizontal: fill in data Vertical: formulas | TOTAL TASKS | CONT. STATUS | CONT. # | CONFIRMED LOADING ? | PICKUP (WEEK IN THE YEAR) | FLOOR/ S | UNITS LOADED | UNIT OTY | CONT. CODE | CONT. SEAL | ESTIMATED LOADING WEEK | LOAD DATE | PACKING SLIPS ? | # DAYS SITTING AT PORT B4 SHIPPED | SHIP DATE | 1ST VESSEL (TO COLOMBIA THEN CALIFORNIA) | 2ND LEG VESSEL ? | 2ND VESSEL (IF ROLLING OVER TO ANOTHER SHIP) | ETA TO LAX PORT? | ETA / DATE TO CALI. PORT. | # DAYS IN SEA | CONFIRMED IN PORT? | ETA TO PHOENIX RR? | DAYS SITTING IN CALI PORT | LOADED ON THE TRAIN | ETA / DATE TO PHOENIX RAILROAD YARD. | IS IT AVIABLE ? (PULLED) | # DAYS FROM PORT TO RAIL YARD | DELIVERY TO JOBSITE? INFO? | DELIVERY DATE | TIME | LOADING AREA | # DAYS SITTING IN THE YARD | # OF YARD DAYS (3 FREE DAYS) | DELIVERY INFO CONFIRMED ? | SENT INSTALL DRAWINGS ? | ARRIVED ON SITE ? | JOBSITE INSTALL DATES | PROJECT STATUS (DELIVERED VS JOBSITE NEEDS) | TOTAL COMMUTE (ITALY TO CHICAGO)
Example | 0 | DEL | 21 | TRUE | WEEK 5 | --- | --- | --- | FCIU7098162 | HLD2682176 | (01/26/26-02/01/26) | 2026-01-27 | TRUE | 12 | 2026-02-08 | GEHARD SCHULTE | TRUE | MAERSK MEMPHIS | TRUE | 2026-03-06 | 26 | TRUE | TRUE | 4 | 2026-03-10 | 2026-03-13 | TRUE | 7 | TRUE | 2026-03-16 | 12:30 | SOUTH DOCK | 3 | 0 | TRUE | TRUE | TRUE | 2026-03-09 | +7 days | 33 | Container was stuck at NY Port, Trump cuts left no one to work for DHS and sub departments that check it in
CTN STS KEY | 11 | PROJ | 1 | FALSE | WEEK 31 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (07/27/26-08/02/26) | 2026-08-06 | FALSE | -4 | 2026-08-02 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-08-27 | 25 | FALSE | FALSE | 8 | 2026-09-04 | 2026-09-09 | FALSE | 13 | FALSE | 2026-09-14 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
Delivered | 11 | PROJ | 2 | FALSE | WEEK 31 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (07/27/26-08/02/26) | 2026-08-06 | FALSE | -4 | 2026-08-02 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-08-27 | 25 | FALSE | FALSE | 8 | 2026-09-04 | 2026-09-09 | FALSE | 13 | FALSE | 2026-09-14 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
Rail Yard | 11 | PROJ | 3 | FALSE | WEEK 34 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (08/17/26-08/23/26) | 2026-08-19 | FALSE | 4 | 2026-08-23 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-09-17 | 25 | FALSE | FALSE | 8 | 2026-09-25 | 2026-09-30 | FALSE | 13 | FALSE | 2026-10-05 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
Train | 11 | PROJ | 4 | FALSE | WEEK 35 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (08/24/26-08/30/26) | 2026-08-26 | FALSE | 4 | 2026-08-30 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-09-24 | 25 | FALSE | FALSE | 8 | 2026-10-02 | 2026-10-07 | FALSE | 13 | FALSE | 2026-10-12 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
In Port | 11 | PROJ | 5 | FALSE | WEEK 36 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (08/31/26-09/06/26) | 2026-09-02 | FALSE | 4 | 2026-09-06 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-10-01 | 25 | FALSE | FALSE | 8 | 2026-10-09 | 2026-10-14 | FALSE | 13 | FALSE | 2026-10-19 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
En Route | 11 | PROJ | 6 | FALSE | WEEK 37 | --- | --- | --- | EDWIN | XXXXXXXXX | (09/07/26-09/13/26) | 2026-09-09 | FALSE | 4 | 2026-09-13 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-10-08 | 25 | FALSE | FALSE | 8 | 2026-10-16 | 2026-10-21 | FALSE | 13 | FALSE | 2026-10-26 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
Loaded | 11 | PROJ | 7 | FALSE | WEEK 38 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (09/14/26-09/20/26) | 2026-09-16 | FALSE | 4 | 2026-09-20 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-10-15 | 25 | FALSE | FALSE | 8 | 2026-10-23 | 2026-10-28 | FALSE | 13 | FALSE | 2026-11-02 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
Loading | 11 | PROJ | 8 | FALSE | WEEK 39 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (09/21/26-09/27/26) | 2026-09-23 | FALSE | 4 | 2026-09-27 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-10-22 | 25 | FALSE | FALSE | 8 | 2026-10-30 | 2026-11-04 | FALSE | 13 | FALSE | 2026-11-09 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
Projected | 11 | PROJ | 9 | FALSE | WEEK 40 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (09/28/26-10/04/26) | 2026-09-30 | FALSE | 4 | 2026-10-04 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-10-29 | 25 | FALSE | FALSE | 8 | 2026-11-06 | 2026-11-11 | FALSE | 13 | FALSE | 2026-11-16 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
| 11 | PROJ | 10 | FALSE | WEEK 41 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (10/05/26-10/11/26) | 2026-10-07 | FALSE | 4 | 2026-10-11 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-11-05 | 25 | FALSE | FALSE | 8 | 2026-11-13 | 2026-11-18 | FALSE | 13 | FALSE | 2026-11-23 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
| 11 | PROJ | 11 | FALSE | WEEK 42 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (10/12/26-10/18/26) | 2026-10-14 | FALSE | 4 | 2026-10-18 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-11-12 | 25 | FALSE | FALSE | 8 | 2026-11-20 | 2026-11-25 | FALSE | 13 | FALSE | 2026-11-30 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
| 11 | PROJ | 12 | FALSE | WEEK 43 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (10/19/26-10/25/26) | 2026-10-21 | FALSE | 4 | 2026-10-25 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-11-19 | 25 | FALSE | FALSE | 8 | 2026-11-27 | 2026-12-02 | FALSE | 13 | FALSE | 2026-12-07 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
| 11 | PROJ | 13 | FALSE | WEEK 44 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (10/26/26-11/01/26) | 2026-10-28 | FALSE | 4 | 2026-11-01 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-11-26 | 25 | FALSE | FALSE | 8 | 2026-12-04 | 2026-12-09 | FALSE | 13 | FALSE | 2026-12-14 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
| 11 | PROJ | 14 | FALSE | WEEK 45 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (11/02/26-11/08/26) | 2026-11-04 | FALSE | 4 | 2026-11-08 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-12-03 | 25 | FALSE | FALSE | 8 | 2026-12-11 | 2026-12-16 | FALSE | 13 | FALSE | 2026-12-21 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
| 11 | PROJ | 15 | FALSE | WEEK 46 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (11/09/26-11/15/26) | 2026-11-11 | FALSE | 4 | 2026-11-15 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-12-10 | 25 | FALSE | FALSE | 8 | 2026-12-18 | 2026-12-23 | FALSE | 13 | FALSE | 2026-12-28 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
| 11 | PROJ | 16 | FALSE | WEEK 47 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (11/16/26-11/22/26) | 2026-11-18 | FALSE | 4 | 2026-11-22 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-12-17 | 25 | FALSE | FALSE | 8 | 2026-12-25 | 2026-12-30 | FALSE | 13 | FALSE | 2027-01-04 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
| 11 | PROJ | 17 | FALSE | WEEK 48 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (11/23/26-11/29/26) | 2026-11-25 | FALSE | 4 | 2026-11-29 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-12-24 | 25 | FALSE | FALSE | 8 | 2027-01-01 | 2027-01-06 | FALSE | 13 | FALSE | 2027-01-11 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
| 11 | PROJ | 18 | FALSE | WEEK 49 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (11/30/26-12/06/26) | 2026-12-02 | FALSE | 4 | 2026-12-06 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2026-12-31 | 25 | FALSE | FALSE | 8 | 2027-01-08 | 2027-01-13 | FALSE | 13 | FALSE | 2027-01-18 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
| 11 | PROJ | 19 | FALSE | WEEK 50 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (12/07/26-12/13/26) | 2026-12-09 | FALSE | 4 | 2026-12-13 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2027-01-07 | 25 | FALSE | FALSE | 8 | 2027-01-15 | 2027-01-20 | FALSE | 13 | FALSE | 2027-01-25 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
| 11 | PROJ | 20 | FALSE | WEEK 51 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (12/14/26-12/20/26) | 2026-12-16 | FALSE | 4 | 2026-12-20 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2027-01-14 | 25 | FALSE | FALSE | 8 | 2027-01-22 | 2027-01-27 | FALSE | 13 | FALSE | 2027-02-01 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | 38 | 0
| 11 | PROJ | 21 | FALSE | WEEK 52 | --- | --- | --- | XXXXXXXXX | XXXXXXXXX | (12/27/27-01/02/28) | 2027-12-29 | FALSE | 4 | 2028-01-02 | XXXXXX XXXX | FALSE | XXXXXX XXXX | FALSE | 2027-01-21 | -346 | FALSE | FALSE | 8 | 2027-01-29 | 2027-02-03 | FALSE | 13 | FALSE | 2027-02-08 | XX PM | XXXXXXX | 5 | 2 | FALSE | FALSE | FALSE | --- |  | -333 | 0

## OMM_Unit Matrix
OPTIMA- BUILDING MATRIX PER UNIT
LIST/ LOOK FULL BREAKDOWN
BUILDING LOGISTICS |  |  |  |  | SHIPPING LOGISTICS | MISALIANIAOUS ROOMS COMPONENTS | [13 empty] | KITCHEN COMPONENETS | [5 empty] | BATHROOM COMPONENTS | [7 empty] | BEDROOM COMPONENTS
[6 empty] | FOYER |  | DEN |  | HALL |  | UTILITY ROOM |  | CLOSET |  | BEV CENTER |  | LAUNDRY CLOSET |  | KITCHEN |  | DINING |  | GREAT ROOM |  | PRIM BATH |  | BATH 2 |  | BATH 3 |  | BATH 4 |  | PRIM BED |  | BED 2 |  | BED 3 |  | BED 4
FLOOR | UNIT # | UNIT | COMBO? | UNIT TYP. | STATUS | STS | CTN | STS | CTN | STS | CTN | STS | CTN | STS | CTN | STS | CTN | STS | CTN | STS | CTN | STS | CTN | STS | CTN | STS | CTN | STS | CTN | STS | CTN | STS | CTN | STS | CTN | STS | CTN | STS | CTN | STS | CTN
FLOOR | UNIT # | UNIT | COMBO? | UNIT TYP | STATUS? | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column24 | Column25 | Column26 | Column27 | Column28 | Column29 | Column30 | Column31 | Column32 | Column33 | Column34 | Column35 | Column36 | Column37 | Column38 | Column39 | Column40 | Column41 | Column42
2 | 1 | 2001 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2 | 2002 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 3 | 2003 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 4 | 2004 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 5 | 2005 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 6 | 2006 | NO | 3B-02 | ORDERED | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | YES | 1 | YES | 1 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
2 | 7 | 2007 | NO | 1B-02 | ORDERED | YES | 1 | NO | 0 | NO | 0 | YES | 1 | NO | 0 | NO | 0 | NO | 0 | YES | 1 | NO | 0 | NO | 0 | YES | 1 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
2 | 8 | 2008 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 9 | 2009 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 10 | 2010 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 11 | 2011 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 12 | 2012 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 13 | 2013 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 14 | 2014 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 15 | 2015 | NO | 3B-04 | ORDERED | YES | 1 | NO | 0 | YES | 1 | YES | 1 | NO | 0 | NO | 0 | NO | 0 | YES | 1 | NO | 0 | NO | 0 | YES | 1 | YES | 1 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
2 | 16 | 2016 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 17 | 2017 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 18 | 2018 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 19 | 2019 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 20 | 2020 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 21 | 2021 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 22 | 2022 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 23 | 2023 | NO | 2B-07 | ORDERED | YES | 1 | NO | 0 | YES | 1 | YES | 1 | NO | 0 | NO | 0 | NO | 0 | YES | 1 | NO | 0 | NO | 0 | YES | 1 | YES | 1 | NO | 0 | NO | 0 | NO | 0 | YES | 1 | NO | 0 | NO | 0
2 | 24 | 2024 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 25 | 2025 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 26 | 2026 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 27 | 2027 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 28 | 2028 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 1 | 3001 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 2 | 3002 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | 3003 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 4 | 3004 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 5 | 3005 | YES | 3005.06.07 | ORDERED | NO | 0 | NO | 0 | NO | 0 | YES | 1 | NO | 0 | NO | 0 | NO | 0 | YES | 1 | YES | 1 | NO | 0 | YES | 1 | YES | 1 | YES | 1 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
3 | 6 | 3006 | YES | 3005.06.07 | ORDERED | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
3 | 7 | 3007 | YES | 3005.06.07 | ORDERED | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
3 | 8 | 3008 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 9 | 3009 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 10 | 3010 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 11 | 3011 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 12 | 3012 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 13 | 3013 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 14 | 3014 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 15 | 3015 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 16 | 3016 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 17 | 3017 | NO | 1B-05 | ORDERED | YES | 2 | NO | 0 | NO | 0 | YES | 2 | NO | 0 | NO | 0 | NO | 0 | YES | 2 | NO | 0 | NO | 0 | YES | 2 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
3 | 18 | 3018 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 19 | 3019 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 20 | 3020 | NO | 1B-06 | ORDERED | YES | 2 | NO | 0 | NO | 0 | YES | 2 | NO | 0 | NO | 0 | NO | 0 | YES | 2 | NO | 0 | NO | 0 | YES | 2 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
3 | 21 | 3021 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 22 | 3022 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 23 | 3023 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 24 | 3024 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 25 | 3025 | NO | 2B-09 | ORDERED | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | YES | 2 | NO | 0 | YES | 2 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
3 | 26 | 3026 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 27 | 3027 | NO | 2B-11 | ORDERED | YES | 2 | NO | 0 | NO | 0 | YES | 2 | NO | 0 | NO | 0 | NO | 0 | YES | 2 | NO | 0 | NO | 0 | YES | 2 | YES | 2 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
3 | 28 | 3028 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 1 | 4001 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 2 | 4002 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 3 | 4003 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 4 | 4004 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 5 | 4005 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 6 | 4006 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 7 | 4007 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 8 | 4008 | NO | 2B-02 | ORDERED | NO | 0 | NO | 0 | NO | 0 | YES | 3 | NO | 0 | NO | 0 | NO | 0 | YES | 3 | NO | 0 | NO | 0 | YES | 3 | YES | 3 | NO | 0 | NO | 0 | NO | 0 | YES | 3 | NO | 0 | NO | 0
4 | 9 | 4009 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 10 | 4010 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 11 | 4011 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 12 | 4012 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 13 | 4013 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 14 | 4014 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 15 | 4015 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 16 | 4016 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 17 | 4017 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 18 | 4018 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 19 | 4019 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 20 | 4020 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 21 | 4021 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 22 | 4022 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 23 | 4023 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 24 | 4024 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 25 | 4025 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 26 | 4026 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 27 | 4027 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 28 | 4028 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 1 | 5001 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 2 | 5002 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 3 | 5003 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 4 | 5004 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 5 | 5005 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 6 | 5006 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 7 | 5007 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 8 | 5008 | YES | 5008.09 | ORDERED | YES | 3 | NO | 0 | NO | 0 | YES | 3 | YES | 3 | NO | 0 | NO | 0 | YES | 3 | NO | 0 | NO | 0 | YES | 3 | YES | 3 | YES | 3 | NO | 0 | NO | 0 | NO | 0 | YES | 3 | NO | 0
5 | 9 | 5009 | YES | 5008.09 | ORDERED | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
5 | 10 | 5010 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 11 | 5011 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 12 | 5012 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 13 | 5013 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 14 | 5014 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 15 | 5015 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 16 | 5016 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 17 | 5017 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 18 | 5018 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 19 | 5019 | NO | 3B-06 | ORDERED | YES | 3 | NO | 0 | NO | 0 | YES | 3 | NO | 0 | YES | 3 | NO | 0 | YES | 3 | NO | 0 | YES | 3 | YES | 3 | YES | 3 | YES | 3 | NO | 0 | NO | 0 | YES | 3 | YES | 3 | NO | 0
5 | 20 | 5020 | NO | 1B-06 | ORDERED | YES | 4 | NO | 0 | NO | 0 | YES | 4 | NO | 0 | NO | 0 | NO | 0 | YES | 4 | NO | 0 | NO | 0 | YES | 4 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
5 | 21 | 5021 | NO | 2B-06 | ORDERED | YES | 4 | NO | 0 | YES | 4 | YES | 4 | NO | 0 | NO | 0 | NO | 0 | YES | 4 | NO | 0 | NO | 0 | YES | 4 | YES | 4 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
5 | 22 | 5022 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 23 | 5023 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 24 | 5024 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 25 | 5025 | NO | 2B-09 | ORDERED | YES | 4 | NO | 0 | NO | 0 | YES | 4 | NO | 0 | NO | 0 | NO | 0 | YES | 4 | NO | 0 | NO | 0 | YES | 4 | YES | 4 | NO | 0 | NO | 0 | NO | 0 | YES | 4 | NO | 0 | NO | 0
5 | 26 | 5026 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 27 | 5027 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 28 | 5028 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 1 | 6001 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 2 | 6002 | YES | 6002.03 | ORDERED | YES | 4 | NO | 0 | NO | 0 | YES | 4 | NO | 0 | NO | 0 | NO | 0 | YES | 4 | NO | 0 | NO | 0 | YES | 4 | YES | 4 | YES | 4 | YES | 4 | NO | 0 | YES | 4 | NO | 0 | NO | 0
6 | 3 | 6003 | YES | 6002.03 | ORDERED | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
6 | 4 | 6004 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 5 | 6005 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 6 | 6006 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 7 | 6007 | NO | 1B-02 | ORDERED | YES | 0 | NO | 0 | NO | 0 | YES | 0 | NO | 0 | NO | 0 | NO | 0 | YES | 0 | NO | 0 | NO | 0 | YES | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
6 | 8 | 6008 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 9 | 6009 | NO | 1B-03 | ORDERED | YES | 0 | NO | 0 | NO | 0 | YES | 0 | NO | 0 | NO | 0 | NO | 0 | YES | 0 | NO | 0 | NO | 0 | YES | 0 | NO | 0 | NO | 0 | NO | 0 | YES | 0 | NO | 0 | NO | 0 | NO | 0
6 | 10 | 6010 | NO | 2B-03 | ORDERED | YES | 0 | NO | 0 | NO | 0 | YES | 0 | NO | 0 | NO | 0 | NO | 0 | YES | 0 | NO | 0 | NO | 0 | YES | 0 | YES | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
6 | 11 | 6011 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 12 | 6012 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 13 | 6013 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 14 | 6014 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 15 | 6015 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 16 | 6016 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 17 | 6017 | YES | 6017.18 | ORDERED | NO | 0 | NO | 0 | NO | 0 | YES | 0 | NO | 0 | NO | 0 | NO | 0 | YES | 0 | NO | 0 | NO | 0 | YES | 0 | YES | 0 | YES | 0 | YES | 0 | NO | 0 | YES | 0 | NO | 0 | NO | 0
6 | 18 | 6018 | YES | 6017.18 | ORDERED | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
6 | 19 | 6019 | YES | 6019.2 | ORDERED | YES | 0 | NO | 0 | NO | 0 | YES | 0 | NO | 0 | YES | 0 | NO | 0 | YES | 0 | NO | 0 | YES | 0 | YES | 0 | YES | 0 | NO | 0 | NO | 0 | NO | 0 | YES | 0 | NO | 0 | NO | 0
6 | 20 | 6020 | YES | 6019.2 | ORDERED | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0 | NO | 0
6 | 21 | 6021 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 22 | 6022 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 23 | 6023 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 24 | 6024 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 25 | 6025 | NO | 2B-09 | ORDERED | YES | 0 | NO | 0 | NO | 0 | YES | 0 | NO | 0 | NO | 0 | NO | 0 | YES | 0 | NO | 0 | NO | 0 | YES | 0 | YES | 0 | NO | 0 | NO | 0 | NO | 0 | YES | 0 | NO | 0 | NO | 0
6 | 26 | 6026 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 27 | 6027 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 28 | 6028 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 1 | 7001 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 2 | 7002 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 3 | 7003 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 4 | 7004 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 5 | 7005 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 6 | 7006 | YES | 7006.07 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 7 | 7007 | YES | 7006.07 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 8 | 7008 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 9 | 7009 | YES | 7009.1 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 10 | 7010 | YES | 7009.1 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 11 | 7011 | NO | 0 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 12 | 7012 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 13 | 7013 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 14 | 7014 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 15 | 7015 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 16 | 7016 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 17 | 7017 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 18 | 7018 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 19 | 7019 | NO | 0 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 20 | 7020 | YES | 7020.21 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 21 | 7021 | YES | 7020.21 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 22 | 7022 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 23 | 7023 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 24 | 7024 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 25 | 7025 | NO | 0 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 26 | 7026 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 27 | 7027 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 28 | 7028 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 1 | 8001 | NO | 0 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 2 | 8002 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 3 | 8003 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 4 | 8004 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 5 | 8005 | YES | 8005.06 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 6 | 8006 | YES | 8005.06 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 7 | 8007 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 8 | 8008 | YES | 8008.09 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 9 | 8009 | YES | 8008.09 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 10 | 8010 | YES | 8010.11 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 11 | 8011 | YES | 8010.11 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 12 | 8012 | NO | 0 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 13 | 8013 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 14 | 8014 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 15 | 8015 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 16 | 8016 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 17 | 8017 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 18 | 8018 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 19 | 8019 | YES | 8019.2 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 20 | 8020 | YES | 8019.2 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 21 | 8021 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 22 | 8022 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 23 | 8023 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 24 | 8024 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 25 | 8025 | YES | 8025.26 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 26 | 8026 | YES | 8025.26 | PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 27 | 8027 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 28 | 8028 | 0 | 0 | NOT IN SCOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 49
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## OMM_Buildout
OPTIMA- JOBSITE BUILDOUT SCHEDULE
DATES PROVIDED BY
TARGET
FLOOR BUILD-OUT SCHEDULE |  |  | OMM SCHEDULE DATES
FLOOR | GROUP # | TOTAL UNITS | FLOOR START DATE | CABINET DELIVERY | SET CABINETS | TOE-KICK INSTALL | FLOOR END DATE
1
2 | 1 | 5 | 2026-09-11 | 2026-09-16 | 2026-09-17 | 2027-04-07 | 2027-04-01
2 | 2 | 5 | 2026-09-17 | 2026-09-21 | 2026-09-22 | 2027-04-07 | 2027-04-06
2 | 3 | 5 | 2026-09-22 | 2026-09-24 | 2026-09-25 | 2027-04-07 | 2027-04-09
2 | 4 | 5 | 2026-09-25 | 2026-09-29 | 2026-09-30 | 2027-04-07 | 2027-04-14
2 | 5 | 5 | 2026-09-30 | 2026-10-02 | 2026-10-05 | 2027-04-07 | 2027-04-19
2 | 6 | 5 | 2026-10-05 | 2026-10-07 | 2026-10-08 | 2027-04-07 | 2027-04-22
3 | 1 | 5 | 2026-10-07 | 2026-10-09 | 2026-10-13 | 2027-05-06 | 2027-04-01
3 | 2 | 5 | 2026-10-12 | 2026-10-14 | 2026-10-16 | 2027-05-06 | 2027-04-06
3 | 3 | 5 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 2027-05-06 | 2027-04-09
3 | 4 | 5 | 2026-10-20 | 2026-10-22 | 2026-10-26 | 2027-05-06 | 2027-04-14
3 | 5 | 5 | 2026-10-23 | 2026-10-27 | 2026-10-29 | 2027-05-06 | 2027-04-19
3 | 6 | 5 | 2026-10-28 | 2026-10-30 | 2026-11-03 | 2027-05-06 | 2027-04-22
4 | 1 | 5 | 2026-10-29 | 2026-11-02 | 2026-11-06 | 2027-05-27 | 2027-04-01
4 | 2 | 5 | 2026-11-03 | 2026-11-05 | 2026-11-11 | 2027-05-27 | 2027-04-06
4 | 3 | 5 | 2026-11-06 | 2026-11-10 | 2026-11-16 | 2027-05-27 | 2027-04-09
4 | 4 | 5 | 2026-11-11 | 2026-11-13 | 2026-11-19 | 2027-05-27 | 2027-04-14
4 | 5 | 5 | 2026-11-16 | 2026-11-18 | 2026-11-24 | 2027-05-27 | 2027-04-19
4 | 6 | 5 | 2026-11-19 | 2026-11-23 | 2026-11-27 | 2027-05-27 | 2027-04-22
5 | 1 | 5 | 2026-11-24 | 2026-11-30 | 2026-12-02 | 2027-06-23 | 2027-04-01
5 | 2 | 5 | 2026-12-01 | 2026-12-03 | 2026-12-07 | 2027-06-23 | 2027-04-06
5 | 3 | 5 | 2026-12-04 | 2026-12-08 | 2026-12-10 | 2027-06-23 | 2027-04-09
5 | 4 | 5 | 2026-12-09 | 2026-12-11 | 2026-12-15 | 2027-06-23 | 2027-04-14
5 | 5 | 5 | 2026-12-14 | 2026-12-16 | 2026-12-18 | 2027-06-23 | 2027-04-19
5 | 6 | 5 | 2026-12-17 | 2026-12-21 | 2026-12-23 | 2027-06-23 | 2027-04-22
6 | 1 | 5 | 2026-12-22 | 2026-12-28 | 2026-12-28 | 2027-07-19 | 2027-04-01
6 | 2 | 5 | 2026-12-29 | 2027-01-04 | 2026-12-31 | 2027-07-19 | 2027-04-06
6 | 3 | 5 | 2027-01-05 | 2027-01-07 | 2027-01-05 | 2027-07-19 | 2027-04-09
6 | 4 | 5 | 2027-01-08 | 2027-01-12 | 2027-01-08 | 2027-07-19 | 2027-04-14
6 | 5 | 5 | 2027-01-13 | 2027-01-15 | 2027-01-13 | 2027-07-19 | 2027-04-19
6 | 6 | 5 | 2027-01-18 | 2027-01-20 | 2027-01-18 | 2027-07-19 | 2027-04-22
7 | 1 | 5 | 2027-01-21 | 2027-01-25 | 2027-01-21 | 2027-08-09 | 2027-04-01
7 | 2 | 5 | 2027-01-26 | 2027-01-28 | 2027-01-26 | 2027-08-09 | 2027-04-06
7 | 3 | 5 | 2027-01-29 | 2027-02-02 | 2027-01-29 | 2027-08-09 | 2027-04-09
7 | 4 | 5 | 2027-02-03 | 2027-02-05 | 2027-02-03 | 2027-08-09 | 2027-04-14
7 | 5 | 5 | 2027-02-08 | 2027-02-10 | 2027-02-08 | 2027-08-09 | 2027-04-19
7 | 6 | 5 | 2027-02-11 | 2027-02-15 | 2027-02-11 | 2027-08-09 | 2027-04-22
8 | 1 | 5 | 2027-02-16 | 2027-02-18 | 2027-02-16 | 2027-08-31 | 2027-04-01
8 | 2 | 5 | 2027-02-19 | 2027-02-23 | 2027-02-19 | 2027-08-31 | 2027-04-06
8 | 3 | 5 | 2027-02-24 | 2027-02-26 | 2027-02-24 | 2027-08-31 | 2027-04-09
8 | 4 | 5 | 2027-03-01 | 2027-03-03 | 2027-03-01 | 2027-08-31 | 2027-04-14
8 | 5 | 5 | 2027-03-04 | 2027-03-08 | 2027-03-04 | 2027-08-31 | 2027-04-19
8 | 6 | 5 | 2027-03-09 | 2027-03-11 | 2027-03-09 | 2027-08-31 | 2027-04-22

## Optima Building Matrix_New Look (hidden)
OPTIMA- ORDER PLACED MATRIX
CONDENSED BUILDING / SCOPE OF WORK
UNITS | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
FLOOR
8
7
6
5
4
3
2
1

## OMM_Container Status
OPTIMA- BUILDING MATRIX | [5 empty] | : COMBO UNIT |  |  | : PROJECTED |  |  | : LOADING |  |  | : LOADED |  |  | : EN ROUTE |  |  | : IN PORT |  |  | : RAILYARD |  |  | : DELIVERED |  |  | : NOT IN SCOPE
CONTAINER STATUS - PER UNIT
PLEASE NOTE: CONTAINERS ARE LISTED PER AREA - (CONTAINER #) ROOM AREA NAME - SEE LEGEND FOR CONTAINER STATUS
UNIT TYPE | 3B-01 | 1B-01 | 2B-01 | 2B-01 | 1B-01 | 3B-02 | 1B-02 | 2B-02 | 1B-03 | 2B-03 | 2B-03 | 1B-04 | 2B-04 | 3B-03 | 3B-04 | 2B-05 | 1B-05 | 3B-05 | 3B-06 | 1B-06 | 2B-06 | 3B-07 | 2B-07 | 2B-08 | 2B-09 | 2B-10 | 2B-11 | 1B-07 | FLOOR-BY-FLOOR LOGISTICS |  |  |  | CTN # | CTNR CODE | STATUS
UNIT # | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 |  |  |  |  | 1 | XXXXXXXXX | PROJ
FLOORS | [32 empty] | 2 | XXXXXXXXX | PROJ
8 | 8001 | 8002 | 8003 | 8004 | 8005 | 8006 | 8007 | 8008 | 8009 | 8010 | 8011 | 8012 | 8013 | 8014 | 8015 | 8016 | 8017 | 8018 | 8019 | 8020 | 8021 | 8022 | 8023 | 8024 | 8025 | 8026 | 8027 | 8028 | 8th FLOOR |  |  |  | 3 | XXXXXXXXX | PROJ
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SCOPE OF WORK (UNITS) |  |  |  | 4 | XXXXXXXXX | PROJ
[29 empty] | UNITs: | 0 |  |  | 5 | XXXXXXXXX | PROJ
[29 empty] | COMBOs: | 0 |  |  | 6 | EDWIN | PROJ
[29 empty] | AREAs: | 0 |  |  | 7 | XXXXXXXXX | PROJ
[29 empty] | DELIVERY TARGET: |  | 2027-02-02 |  | 8 | XXXXXXXXX | PROJ
[33 empty] | 9 | XXXXXXXXX | PROJ
[29 empty] | SCOPE OF WORK (DELIVERY STATUS) |  |  |  | 10 | XXXXXXXXX | PROJ
[29 empty] | 0 | OUT OF | 0 | 0% | 11 | XXXXXXXXX | PROJ
[29 empty] | 0 | OUT OF | 0 | 0% | 12 | XXXXXXXXX | PROJ
[29 empty] | 0 | OUT OF | 0 | 0% | 13 | XXXXXXXXX | PROJ
7 | 7001 | 7002 | 7003 | 7004 | 7005 | 7006 | 7007 | 7008 | 7009 | 7010 | 7011 | 7012 | 7013 | 7014 | 7015 | 7016 | 7017 | 7018 | 7019 | 7020 | 7021 | 7022 | 7023 | 7024 | 7025 | 7026 | 7027 | 7028 | 7th FLOOR |  |  |  | 14 | XXXXXXXXX | PROJ
[29 empty] | SCOPE OF WORK (UNITS) |  |  |  | 15 | XXXXXXXXX | PROJ
[29 empty] | UNITs: | 0 |  |  | 16 | XXXXXXXXX | PROJ
[29 empty] | COMBOs: | 0 |  |  | 17 | XXXXXXXXX | PROJ
[29 empty] | AREAs: | 0 |  |  | 18 | XXXXXXXXX | PROJ
[29 empty] | DELIVERY TARGET: |  | 2027-01-07 |  | 19 | XXXXXXXXX | PROJ
[33 empty] | 20 | XXXXXXXXX | PROJ
[29 empty] | SCOPE OF WORK (DELIVERY STATUS) |  |  |  | 21 | XXXXXXXXX | PROJ
[29 empty] | 0 | OUT OF | 0 | 0%
[29 empty] | 0 | OUT OF | 0 | 0%
[29 empty] | 0 | OUT OF | 0 | 0%
6 | 6001 | 6002 | 6003 | 6004 | 6005 | 6006 | 6007 | 6008 | 6009 | 6010 | 6011 | 6012 | 6013 | 6014 | 6015 | 6016 | 6017 | 6018 | 6019 | 6020 | 6021 | 6022 | 6023 | 6024 | 6025 | 6026 | 6027 | 6028 | 6th FLOOR
|  | (4) FOYER |  |  |  |  | FOYER |  | FOYER | FOYER | [6 empty] | UTILITY ROOM |  | FOYER | [5 empty] | FOYER |  |  |  | SCOPE OF WORK (UNITS)
|  | (4) UTILITY ROOM |  |  |  |  | UTILITY ROOM |  | UTILITY ROOM | UTILITY ROOM | [6 empty] | KITCHEN |  | UTILITY ROOM | [5 empty] | UTILITY ROOM |  |  |  | UNITs: | 0
|  | (4) KITCHEN |  |  |  |  | KITCHEN |  | KITCHEN | KITCHEN | [6 empty] | PRIM BATH |  | BEV CENTER | [5 empty] | KITCHEN |  |  |  | COMBOs: | 0
|  | (4) PRIM BATH |  |  |  |  | PRIM BATH |  | PRIM BATH | PRIM BATH | [6 empty] | BATH 2 |  | KITCHEN | [5 empty] | PRIM BATH |  |  |  | AREAs: | 0
|  | (4) BATH 2 | [6 empty] | PRIM BED | BATH 2 | [6 empty] | BATH 3 |  | GREAT ROOM | [5 empty] | BATH 2 |  |  |  | DELIVERY TARGET: |  | 2026-12-14
|  | (4) BATH 3 | [14 empty] | BATH 4 |  | PRIM BATH | [5 empty] | BED 2
|  | (4) BATH 4 | [14 empty] | BED 2 |  | BATH 2 | [9 empty] | SCOPE OF WORK (DELIVERY STATUS)
|  | (4) BED 2 | [16 empty] | BED 2 | [9 empty] | 0 | OUT OF | 0 | 0%
[29 empty] | 0 | OUT OF | 0 | 0%
[29 empty] | 0 | OUT OF | 0 | 0%
5 | 5001 | 5002 | 5003 | 5004 | 5005 | 5006 | 5007 | 5008 | 5009 | 5010 | 5011 | 5012 | 5013 | 5014 | 5015 | 5016 | 5017 | 5018 | 5019 | 5020 | 5021 | 5022 | 5023 | 5024 | 5025 | 5026 | 5027 | 5028 | 5th FLOOR
[8 empty] | (3) FOYER | [10 empty] | (3) FOYER | (4) FOYER | (4) FOYER |  |  |  | (4) FOYER |  |  |  | SCOPE OF WORK (UNITS)
[8 empty] | (3) UTILITY ROOM | [10 empty] | (3) UTILITY ROOM | (4) UTILITY ROOM | (4) HALL |  |  |  | (4) UTILITY ROOM |  |  |  | UNITs: | 0
[8 empty] | (3) CLOSET | [10 empty] | (3) BEV CENTER | (4) KITCHEN | (4) UTILITY ROOM |  |  |  | (4) KITCHEN |  |  |  | COMBOs: | 0
[8 empty] | (3) KITCHEN | [10 empty] | (3) KITCHEN | (4) PRIM BATH | (4) KITCHEN |  |  |  | (4) PRIM BATH |  |  |  | AREAs: | 0
[8 empty] | (3) PRIM BATH | [10 empty] | (3) GREAT ROOM |  | (4) PRIM BATH |  |  |  | (4) BATH 2 |  |  |  | DELIVERY TARGET: |  | 2026-11-18
[8 empty] | (3) BATH 2 | [10 empty] | (3) PRIM BATH |  | (4) BATH 2 |  |  |  | (4) BED 2
[8 empty] | (3) BATH 3 | [10 empty] | (3) BATH 2 | [9 empty] | SCOPE OF WORK (DELIVERY STATUS)
[8 empty] | (3) BED 3 | [10 empty] | (3) BATH 3 | [9 empty] | 0 | OUT OF | 0 | 0%
[19 empty] | (3) BED 2 | [9 empty] | 0 | OUT OF | 0 | 0%
[19 empty] | (3) BED 3 | [9 empty] | 0 | OUT OF | 0 | 0%
4 | 4001 | 4002 | 4003 | 4004 | 4005 | 4006 | 4007 | 4008 | 4009 | 4010 | 4011 | 4012 | 4013 | 4014 | 4015 | 4016 | 4017 | 4018 | 4019 | 4020 | 4021 | 4022 | 4023 | 4024 | 4025 | 4026 | 4027 | 4028 | 4th FLOOR
[8 empty] | (3) UTILITY ROOM | [20 empty] | SCOPE OF WORK (UNITS)
[8 empty] | (3) KITCHEN | [20 empty] | UNITs: | 1
[8 empty] | (3) PRIM BATH | [20 empty] | COMBOs: | 0
[8 empty] | (3) BATH 2 | [20 empty] | AREAs: | 5
[8 empty] | (3) BED 2 | [20 empty] | DELIVERY TARGET: |  | 2026-10-23
SCOPE OF WORK (DELIVERY STATUS)
[29 empty] | 0 | OUT OF | 5 | 0%
[29 empty] | 0 | OUT OF | 1 | 0%
[29 empty] | 0 | OUT OF | 0 | 0%
3 | 3001 | 3002 | 3003 | 3004 | 3005 | 3006 | 3007 | 3008 | 3009 | 3010 | 3011 | 3012 | 3013 | 3014 | 3015 | 3016 | 3017 | 3018 | 3019 | 3020 | 3021 | 3022 | 3023 | 3024 | 3025 | 3026 | 3027 | 3028 | 3th FLOOR
[5 empty] | (1) UTILITY ROOM | [11 empty] | (2) FOYER |  |  | (2) FOYER |  |  |  |  | (2) BEV CENTER |  | (2) FOYER |  | SCOPE OF WORK (UNITS)
[5 empty] | (1) KITCHEN | [11 empty] | (2) UTILITY ROOM |  |  | (2) UTILITY ROOM |  |  |  |  | (2) KITCHEN |  | (2) UTILITY ROOM |  | UNITs: | 5
[5 empty] | (1) DINING | [11 empty] | (2) KITCHEN |  |  | (2) KITCHEN | [6 empty] | (2) KITCHEN |  | COMBOs: | 1
[5 empty] | (1) PRIM BATH | [11 empty] | (2) PRIM BATH |  |  | (2) PRIM BATH | [6 empty] | (2) PRIM BATH |  | AREAs: | 21
[5 empty] | (1) BATH 2 | [21 empty] | (2) BATH 2 |  | DELIVERY TARGET: |  | 2026-09-29
(1) BATH 3
SCOPE OF WORK (DELIVERY STATUS)
[29 empty] | 0 | OUT OF | 21 | 0%
[29 empty] | 0 | OUT OF | 5 | 0%
[29 empty] | 0 | OUT OF | 1 | 0%
2 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2th FLOOR
[6 empty] | (1) BEV CENTER | (1) FOYER | [7 empty] | (1) FOYER | [7 empty] | (1) FOYER | [5 empty] | SCOPE OF WORK (UNITS)
[6 empty] | (1) LAUNDRY CLOSET | (1) UTILITY ROOM | [7 empty] | (1) HALL | [7 empty] | (1) HALL | [5 empty] | UNITs: | 4
[7 empty] | (1) KITCHEN | [7 empty] | (1) UTILITY ROOM | [7 empty] | (1) UTILITY ROOM | [5 empty] | COMBOs: | 0
[7 empty] | (1) PRIM BATH | [7 empty] | (1) KITCHEN | [7 empty] | (1) KITCHEN | [5 empty] | AREAs: | 19
[15 empty] | (1) PRIM BATH | [7 empty] | (1) PRIM BATH | [5 empty] | DELIVERY TARGET: |  | 2026-09-03
[15 empty] | (1) BATH 2 | [7 empty] | (1) BATH 2
[23 empty] | (1) BED 2 | [5 empty] | SCOPE OF WORK (DELIVERY STATUS)
[29 empty] | 0 | OUT OF | 19 | 0%
[29 empty] | 0 | OUT OF | 4 | 0%
[29 empty] | 0 | OUT OF | 0 | 0%
0
Note on AF16: Author: Counts areas in C75:AD84 whose container status = DEL (delivered). Status pulled via the (#) in each cell -> helper AO6:AQ26. Change "DEL" if your delivered code differs.
Note on AH16: Author: Total areas in scope = count of non-blank cells in C75:AD84.
Note on AF27: Author: Counts areas in C75:AD84 whose container status = DEL (delivered). Status pulled via the (#) in each cell -> helper AO6:AQ26. Change "DEL" if your delivered code differs.
Note on AH27: Author: Total areas in scope = count of non-blank cells in C75:AD84.
Note on AF38: Author: Counts areas in C75:AD84 whose container status = DEL (delivered). Status pulled via the (#) in each cell -> helper AO6:AQ26. Change "DEL" if your delivered code differs.
Note on AH38: Author: Total areas in scope = count of non-blank cells in C75:AD84.
Note on AF49: Author: Counts areas in C75:AD84 whose container status = DEL (delivered). Status pulled via the (#) in each cell -> helper AO6:AQ26. Change "DEL" if your delivered code differs.
Note on AH49: Author: Total areas in scope = count of non-blank cells in C75:AD84.
Note on AF60: Author: Counts areas in C75:AD84 whose container status = DEL (delivered). Status pulled via the (#) in each cell -> helper AO6:AQ26. Change "DEL" if your delivered code differs.
Note on AH60: Author: Total areas in scope = count of non-blank cells in C75:AD84.
Note on AF71: Author: Counts areas in C75:AD84 whose container status = DEL (delivered). Status pulled via the (#) in each cell -> helper AO6:AQ26. Change "DEL" if your delivered code differs.
Note on AH71: Author: Total areas in scope = count of non-blank cells in C75:AD84.
Note on AF82: Author: Counts areas in C75:AD84 whose container status = DEL (delivered). Status pulled via the (#) in each cell -> helper AO6:AQ26. Change "DEL" if your delivered code differs.
Note on AH82: Author: Total areas in scope = count of non-blank cells in C75:AD84.

## OMM_Building Matrix
OPTIMA- BUILDING MATRIX | [5 empty] | : COMBO UNIT |  |  | : NOT IN SCOPE |  |  | : ORDER SUMBMITTED |  |  |  | : PENDING ORDER |  |  |  | : TARGET DATE
ORDER STATUS - PER UNIT
UNIT TYPE | 3B-01 | 1B-01 | 2B-01 | 2B-01 | 1B-01 | 3B-02 | 1B-02 | 2B-02 | 1B-03 | 2B-03 | 2B-03 | 1B-04 | 2B-04 | 3B-03 | 3B-04 | 2B-05 | 1B-05 | 3B-05 | 3B-06 | 1B-06 | 2B-06 | 3B-07 | 2B-07 | 2B-08 | 2B-09 | 2B-10 | 2B-11 | 1B-07 | FLOOR-BY-FLOOR LOGISTICS
UNIT # | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
FLOORS
8 | 8001 | 8002 | 8003 | 8004 | 8005 | 8006 | 8007 | 8008 | 8009 | 8010 | 8011 | 8012 | 8013 | 8014 | 8015 | 8016 | 8017 | 8018 | 8019 | 8020 | 8021 | 8022 | 8023 | 8024 | 8025 | 8026 | 8027 | 8028 | 8th FLOOR
SCOPE OF WORK:
[29 empty] | SCOPE OF WORK: | 0 AREAS TO DELIVER
[29 empty] | UNITS IN SCOPE: | 0 UNITS (0 COMBO)
DELIVERY SCHEDULE
[29 empty] | DELIVERY GR 1: | 2027-02-18
[29 empty] | DELIVERY GR 2: | 2027-02-23
[29 empty] | DELIVERY GR 3: | 2027-02-26
[29 empty] | DELIVERY GR 4: | 2027-03-03
[29 empty] | DELIVERY GR 5: | 2027-03-08
[29 empty] | DELIVERY GR 6: | 2027-03-11
7 | 7001 | 7002 | 7003 | 7004 | 7005 | 7006 | 7007 | 7008 | 7009 | 7010 | 7011 | 7012 | 7013 | 7014 | 7015 | 7016 | 7017 | 7018 | 7019 | 7020 | 7021 | 7022 | 7023 | 7024 | 7025 | 7026 | 7027 | 7028 | 7th FLOOR
SCOPE OF WORK:
[29 empty] | SCOPE OF WORK: | 0 AREAS TO DELIVER
[29 empty] | UNITS IN SCOPE: | 0 UNITS (0 COMBO)
DELIVERY SCHEDULE
[29 empty] | DELIVERY GR 1: | 2027-01-25
[29 empty] | DELIVERY GR 2: | 2027-01-28
[29 empty] | DELIVERY GR 3: | 2027-02-02
[29 empty] | DELIVERY GR 4: | 2027-02-05
[29 empty] | DELIVERY GR 5: | 2027-02-10
[29 empty] | DELIVERY GR 6: | 2027-02-15
6 | 6001 | 6002 | 6003 | 6004 | 6005 | 6006 | 6007 | 6008 | 6009 | 6010 | 6011 | 6012 | 6013 | 6014 | 6015 | 6016 | 6017 | 6018 | 6019 | 6020 | 6021 | 6022 | 6023 | 6024 | 6025 | 6026 | 6027 | 6028 | 6th FLOOR
|  | FOYER |  |  |  |  | FOYER |  | FOYER | FOYER | [6 empty] | UTILITY ROOM |  | FOYER | [5 empty] | FOYER |  |  |  | SCOPE OF WORK:
|  | UTILITY ROOM |  |  |  |  | UTILITY ROOM |  | UTILITY ROOM | UTILITY ROOM | [6 empty] | KITCHEN |  | UTILITY ROOM | [5 empty] | UTILITY ROOM |  |  |  | SCOPE OF WORK: | 43 AREAS TO DELIVER
|  | KITCHEN |  |  |  |  | KITCHEN |  | KITCHEN | KITCHEN | [6 empty] | PRIM BATH |  | BEV CENTER | [5 empty] | KITCHEN |  |  |  | UNITS IN SCOPE: | 7 UNITS (3 COMBO)
|  | PRIM BATH |  |  |  |  | PRIM BATH |  | PRIM BATH | PRIM BATH | [6 empty] | BATH 2 |  | KITCHEN | [5 empty] | PRIM BATH |  |  |  | DELIVERY SCHEDULE
|  | BATH 2 | [6 empty] | PRIM BED | BATH 2 | [6 empty] | BATH 3 |  | GREAT ROOM | [5 empty] | BATH 2 |  |  |  | DELIVERY GR 1: | 2026-12-28
|  | BATH 3 | [14 empty] | BATH 4 |  | PRIM BATH | [5 empty] | BED 2 |  |  |  | DELIVERY GR 2: | 2027-01-04
|  | BATH 4 | [14 empty] | BED 2 |  | BATH 2 | [9 empty] | DELIVERY GR 3: | 2027-01-07
|  | BED 2 | [16 empty] | BED 2 | [9 empty] | DELIVERY GR 4: | 2027-01-12
[29 empty] | DELIVERY GR 5: | 2027-01-15
[29 empty] | DELIVERY GR 6: | 2027-01-20
5 | 5001 | 5002 | 5003 | 5004 | 5005 | 5006 | 5007 | 5008 | 5009 | 5010 | 5011 | 5012 | 5013 | 5014 | 5015 | 5016 | 5017 | 5018 | 5019 | 5020 | 5021 | 5022 | 5023 | 5024 | 5025 | 5026 | 5027 | 5028 | 5th FLOOR
[8 empty] | FOYER | [10 empty] | FOYER | FOYER | FOYER |  |  |  | FOYER |  |  |  | SCOPE OF WORK:
[8 empty] | UTILITY ROOM | [10 empty] | UTILITY ROOM | UTILITY ROOM | HALL |  |  |  | UTILITY ROOM |  |  |  | SCOPE OF WORK: | 34 AREAS TO DELIVER
[8 empty] | CLOSET | [10 empty] | BEV CENTER | KITCHEN | UTILITY ROOM |  |  |  | KITCHEN |  |  |  | UNITS IN SCOPE: | 5 UNITS (1 COMBO)
[8 empty] | KITCHEN | [10 empty] | KITCHEN | PRIM BATH | KITCHEN |  |  |  | PRIM BATH |  |  |  | DELIVERY SCHEDULE
[8 empty] | PRIM BATH | [10 empty] | GREAT ROOM |  | PRIM BATH |  |  |  | BATH 2 |  |  |  | DELIVERY GR 1: | 2026-11-30
[8 empty] | BATH 2 | [10 empty] | PRIM BATH |  | BATH 2 |  |  |  | BED 2 |  |  |  | DELIVERY GR 2: | 2026-12-03
[8 empty] | BATH 3 | [10 empty] | BATH 2 | [9 empty] | DELIVERY GR 3: | 2026-12-08
[8 empty] | BED 3 | [10 empty] | BATH 3 | [9 empty] | DELIVERY GR 4: | 2026-12-11
[19 empty] | BED 2 | [9 empty] | DELIVERY GR 5: | 2026-12-16
[19 empty] | BED 3 | [9 empty] | DELIVERY GR 6: | 2026-12-21
4 | 4001 | 4002 | 4003 | 4004 | 4005 | 4006 | 4007 | 4008 | 4009 | 4010 | 4011 | 4012 | 4013 | 4014 | 4015 | 4016 | 4017 | 4018 | 4019 | 4020 | 4021 | 4022 | 4023 | 4024 | 4025 | 4026 | 4027 | 4028 | 4th FLOOR
[8 empty] | UTILITY ROOM | [20 empty] | SCOPE OF WORK:
[8 empty] | KITCHEN | [20 empty] | SCOPE OF WORK: | 5 AREAS TO DELIVER
[8 empty] | PRIM BATH | [20 empty] | UNITS IN SCOPE: | 1 UNITS (0 COMBO)
[8 empty] | BATH 2 | [20 empty] | DELIVERY SCHEDULE
[8 empty] | BED 2 | [20 empty] | DELIVERY GR 1: | 2026-11-02
[29 empty] | DELIVERY GR 2: | 2026-11-05
[29 empty] | DELIVERY GR 3: | 2026-11-10
[29 empty] | DELIVERY GR 4: | 2026-11-13
[29 empty] | DELIVERY GR 5: | 2026-11-18
[29 empty] | DELIVERY GR 6: | 2026-11-23
3 | 3001 | 3002 | 3003 | 3004 | 3005 | 3006 | 3007 | 3008 | 3009 | 3010 | 3011 | 3012 | 3013 | 3014 | 3015 | 3016 | 3017 | 3018 | 3019 | 3020 | 3021 | 3022 | 3023 | 3024 | 3025 | 3026 | 3027 | 3028 | 3th FLOOR
[5 empty] | UTILITY ROOM | [11 empty] | FOYER |  |  | FOYER |  |  |  |  | BEV CENTER |  | FOYER |  | SCOPE OF WORK:
[5 empty] | KITCHEN | [11 empty] | UTILITY ROOM |  |  | UTILITY ROOM |  |  |  |  | KITCHEN |  | UTILITY ROOM |  | SCOPE OF WORK: | 21 AREAS TO DELIVER
[5 empty] | DINING | [11 empty] | KITCHEN |  |  | KITCHEN | [6 empty] | KITCHEN |  | UNITS IN SCOPE: | 5 UNITS (1 COMBO)
[5 empty] | PRIM BATH | [11 empty] | PRIM BATH |  |  | PRIM BATH | [6 empty] | PRIM BATH |  | DELIVERY SCHEDULE
[5 empty] | BATH 2 | [21 empty] | BATH 2 |  | DELIVERY GR 1: | 2026-10-09
[5 empty] | BATH 3 | [23 empty] | DELIVERY GR 2: | 2026-10-14
[29 empty] | DELIVERY GR 3: | 2026-10-19
[29 empty] | DELIVERY GR 4: | 2026-10-22
[29 empty] | DELIVERY GR 5: | 2026-10-27
[29 empty] | DELIVERY GR 6: | 2026-10-30
2 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2th FLOOR
[6 empty] | BEV CENTER | FOYER | [7 empty] | FOYER | [7 empty] | FOYER | [5 empty] | SCOPE OF WORK:
[6 empty] | LAUNDRY CLOSET | UTILITY ROOM | [7 empty] | HALL | [7 empty] | HALL | [5 empty] | SCOPE OF WORK: | 19 AREAS TO DELIVER
[7 empty] | KITCHEN | [7 empty] | UTILITY ROOM | [7 empty] | UTILITY ROOM | [5 empty] | UNITS IN SCOPE: | 4 UNITS (0 COMBO)
[7 empty] | PRIM BATH | [7 empty] | KITCHEN | [7 empty] | KITCHEN | [5 empty] | DELIVERY SCHEDULE
[15 empty] | PRIM BATH | [7 empty] | PRIM BATH | [5 empty] | DELIVERY GR 1: | 2026-09-16
[15 empty] | BATH 2 | [7 empty] | BATH 2 | [5 empty] | DELIVERY GR 2: | 2026-09-21
[23 empty] | BED 2 | [5 empty] | DELIVERY GR 3: | 2026-09-24
[29 empty] | DELIVERY GR 4: | 2026-09-29
[29 empty] | DELIVERY GR 5: | 2026-10-02
[29 empty] | DELIVERY GR 6: | 2026-10-07
0